| Task | Start Date | Duration | End Date |
| --- | --- | --- | --- |
| Literature Review | 1/1/2025 | 3 months | 31/03/2025 |
| First Publication | 1/4/2025 | 3 months | 30/06/2025 |
| Data Collection | 1/4/2025 | 4 months | 31/07/2025 |
| Data Analysis | 1/8/2025 | 2 months | 30/09/2025 |
| Model Development | 1/10/2025 | 3 months | 31/12/2025 |
| Model Evaluation | 1/1/2026 | 2 months | 29/02/2026 |
| First Conference Paper | 1/3/2026 | 2 months | 30/04/2026 |
| Model Optimization | 1/3/2026 | 3 months | 31/05/2026 |
| Second Conference Paper | 1/6/2026 | 3 months | 31/08/2026 |
| Comparison and Analysis | 1/9/2026 | 3 months | 30/11/2026 |
| Second Publication | 1/1/2027 | 3 months | 31/03/2027 |
| Writing and Dissemination | 1/11/2027 | 11 months | 30/09/2028 |