Ethiopian Public Health Institute

National Public Health Emergency

Operations Center (PHEOC)

SIMULATION EXERCISE REPORT

ET-MRR Functional Simulation Exercise

August, 2025

Addis Ababa, Ethiopia

Contents

Acknowledgement	ii

Executive Summary	iii

Introduction	1

Rationale	2

Scope	3

Aims and Objectives	4

Methodology	5

Major Findings	9

Conclusion from the Findings	16

Recommendations for the identified gaps	17

Annexes	19

Annex 1: Action Plan for Improvement of Identified Gaps	19

Annex 2: National Exercise Management Team	21

Annex 3: National Exercise participants	22

Annex 4: National exercise management team deployed to regions	23

Annex 5: Regional Exercise participants	24

Annex 6: Exercise agenda	30

Annex 7: Budget for exercise conduct	31

Annex 8: Participant Feedback form	32

Annex 9: Exercise evaluation form for observer	34

# Acknowledgement

We would like to express our sincere appreciation to all national and regional participants, facilitators, evaluators, and support staff who contributed to the successful conduct of this simulation exercise.

Your dedication, professionalism, and commitment to improve our preparedness and response capabilities have been invaluable. The time and effort you invested in planning, executing, and evaluating this exercise have provided critical insights that will strengthen our operational readiness.

We also acknowledge the cooperation and support of WHO and UKHSA, whose collaboration, technical and financial support made this exercise possible.

This activity has not only tested our plans and procedures but also fostered stronger teamwork, communication, and resilience across all involved regions and sectors.

We also wish to give special recognition to our partner-UKHSA whose collaboration and financial support ensured the smooth conduct of this exercise. Your contributions have been instrumental in strengthening our preparedness and response capacity.

# Executive Summary

The ET_MRR_2025 conducted from 24-27 July 2025 G.C at Ethiopian Public Health Institute National Public Health Emergency Operations Center (PHEOC), was designed to test and evaluate the national and regional PHEOCs preparedness, coordination, and response capabilities in the event of multi emergency situation

The exercise adopted a Hybrid simulation format, incorporating discussions based and, functional coordination activities. This format allowed participants to engage in both strategic decision-making and practical, hands-on response activities.

The simulation exercise successfully met its primary objectives and provided valuable insights into both strengths and areas for improvement. The lessons learned will guide the refinement of plans, training programs, and operational procedures to ensure greater resilience and readiness in future real-world incidents.

# Introduction

The Ethiopian Public Health Institute (EPHI), in collaboration with regional health authorities and international partners, conducted a comprehensive multi-outbreak functional simulation exercise from June 24 to 27, 2025. This exercise represented a critical milestone in Ethiopia's ongoing efforts to strengthen public health emergency preparedness and response capabilities at both national and sub-national levels.

Ethiopia faces a complex landscape of public health challenges, including recurrent outbreaks of cholera, malnutrition, measles, and emerging threats such as COVID-19 and Mpox. The country's diverse geography, population mobility patterns, cross-border dynamics, and varying levels of health system capacity create unique vulnerabilities that require robust and coordinated emergency response mechanisms. Recent global health emergencies have underscored the importance of having well-tested, functional emergency operations centres that can effectively coordinate multi-sectoral responses to complex health threats.

The simulation exercise was designed as a functional exercise that tested real-time decision-making, coordination mechanisms, and operational procedures across Ethiopia's network of Public Health Emergency Operations Centres (PHEOCs). Unlike tabletop exercises that focus primarily on discussion and planning, this functional exercise required participants to actively implement response procedures, utilize communication systems, and coordinate resources as they would during an actual emergency.

The exercise scenario centred on multiple concurrent outbreaks affecting different regions of Ethiopia, specifically focusing on Mpox, Rabies, and Rift Valley Fever. This multi-outbreak approach was deliberately chosen to test the system's capacity to manage complex emergencies that strain resources and require sophisticated coordination mechanisms. The scenario began with early signals of disease activity in border regions and progressively escalated to involve multiple regions, testing both vertical coordination between national and regional levels and horizontal coordination among different regions and sectors.

Participation in the exercise was extensive, involving the National PHEOC at EPHI, thirteen regional PHEOCs, and key stakeholders from various government sectors including the Ministry of Health, National Disaster Risk Management Commission, and Animal Health Institute. International partners including the World Health Organization, Centers for Disease Control and Prevention, UK Health Security Agency, and Ohio State University Global One Health Initiative provided technical support and evaluation expertise.

The exercise was conducted using a hybrid approach that combined in-person activities at regional PHEOCs with virtual coordination mechanisms, reflecting the realities of emergency response in a geographically diverse country. This approach enabled broad participation while testing the technological infrastructure and communication protocols that are essential for effective emergency coordination.

# Rationale

The rationale for conducting this multi-outbreak functional simulation exercise stems from several critical factors that underscore the importance of robust public health emergency preparedness in Ethiopia. The country's strategic location in the Horn of Africa, its role as a major hub for international travel and trade, and its complex epidemiological profile create conditions where public health emergencies can have both national and international implications.

Recent global experiences with COVID-19, ongoing challenges with endemic diseases, and the emergence of new health threats such as Mpox have demonstrated that traditional single-disease response approaches are insufficient for addressing the complex, multi-faceted emergencies that characterize modern public health challenges. The declaration of Mpox as a Public Health Emergency of International Concern by the World Health Organization in August 2024 highlighted the need for countries to have robust systems capable of detecting, assessing, and responding to emerging health threats while maintaining capacity to address ongoing health challenges.

Ethiopia's federal structure, with its network of regional health systems operating under national coordination, requires sophisticated mechanisms for information sharing, resource coordination, and decision-making across multiple levels of government. The country's experience with various outbreaks has revealed both strengths and gaps in these coordination mechanisms, making it essential to test and refine these systems through realistic simulation exercises.

The One Health approach, which recognizes the interconnection between human, animal, and environmental health, is particularly relevant in the Ethiopian context where zoonotic diseases represent a significant proportion of public health threats. Approximately seventy percent of emerging infectious diseases are of zoonotic origin, making cross-sectoral coordination between human health, animal health, and environmental sectors essential for effective prevention and response.

Furthermore, Ethiopia's commitment to the International Health Regulations (2005) requires the country to maintain core capacities for detecting, assessing, notifying, and responding to public health emergencies. Simulation exercises are recognized as one of the four key tools for monitoring and evaluating these capacities, providing opportunities to test systems, identify gaps, and implement improvements before actual emergencies occur.

# Scope

The scope of the ET MRR Functional Simulation Exercise encompassed multiple dimensions of public health emergency response, testing capabilities across geographic, organizational, and functional boundaries. Geographically, the exercise involved the National PHEOC and thirteen regional PHEOCs, representing the full spectrum of Ethiopia's federal health system structure. This comprehensive geographic coverage enabled testing of coordination mechanisms across different contexts, from densely populated urban areas to remote pastoral regions, each with distinct challenges and capacities.

The temporal scope of the exercise compressed approximately six months of emergency response activities into four intensive days, utilizing time jumps to simulate the evolution of outbreaks from initial detection through peak response and eventual de-escalation. This compressed timeline enabled participants to experience the full cycle of emergency response while maintaining the intensity and decision-making pressure characteristic of actual emergencies.

Functionally, the exercise tested all core components of the Incident Management System, including command and control, operations, planning, logistics, and finance and administration. The simulation specifically focused on testing coordination mechanisms between national and regional levels, information management and sharing systems, communication technologies, and the implementation of public health measures including surveillance, laboratory confirmation, case management, infection prevention and control, and risk communication and community engagement.

The exercise incorporated a multi-hazard approach, simulating concurrent outbreaks of Mpox, Rabies, and Rift Valley Fever to test the system's capacity to manage complex emergencies that require different types of responses and involve different sectors. This approach reflected the reality that public health systems must be prepared to address multiple threats simultaneously, particularly in contexts where baseline health challenges create ongoing demands on system capacity.

Organizationally, the scope included testing coordination mechanisms with key government sectors beyond health, including disaster management, animal health, and security sectors. The exercise also tested engagement with international partners and humanitarian organizations, reflecting the multi-sectoral nature of effective emergency response.

The One Health approach was integrated throughout the exercise scope, testing coordination mechanisms between human health, animal health, and environmental health sectors. This was particularly relevant for the zoonotic diseases included in the scenario and reflected Ethiopia's commitment to implementing integrated approaches to health security.

# Aims and Objectives

The ET MRR Functional Simulation Exercise was designed with specific aims and objectives that aligned with Ethiopia's national priorities for health security and international commitments under the International Health Regulations. The overarching aim was to assess and enhance the preparedness and operational readiness of Ethiopia's Public Health Emergency Operations Centers in responding to complex, multi-outbreak scenarios.

The primary objectives of the exercise were:

- To assess the operationalization of key plans and procedures of emergency management at both national and regional levels, including testing the effectiveness of existing standard operating procedures, guidelines, and protocols in realistic emergency scenarios.

- To evaluate coordination and collaboration mechanisms between the national PHEOC and regional PHEOCs, as well as coordination with partners and other relevant sectors, ensuring that information flows effectively and decisions are made in a timely and coordinated manner.

- To assess information sharing and management capabilities, specifically testing the systems and procedures for managing incident-specific data, event management information, and contextual data that supports evidence-based decision-making during emergencies.

- To determine PHEOC-to-PHEOC communication and technology use capabilities, testing both the technical infrastructure and operational procedures that enable effective communication and coordination during public health emergencies.

- To test the capacity of public health measures including screening, surveillance, risk communication and community engagement, infection prevention and control, and case management, particularly in the context of multi-outbreak PHEOC activation.

To develop practical action plans that support the operationalization of standard PHEOC activities through a One Health approach, ensuring that lessons learned from the exercise translate into concrete improvements in emergency preparedness and response capabilities.

# Methodology

Exercise Design

The ET MRR Functional Simulation Exercise was designed as a comprehensive functional exercise that tested real-time decision-making and operational capabilities across Ethiopia's network of Public Health Emergency Operations Centers. The exercise design incorporated several key elements that distinguished it from other types of emergency preparedness activities.

The scenario was developed to be realistic and challenging, incorporating multiple concurrent outbreaks that would test the system's capacity to manage complex emergencies. The multi-outbreak approach was specifically chosen to reflect the reality that public health systems must be prepared to address multiple threats simultaneously, particularly in contexts where baseline health challenges create ongoing demands on system capacity.

The exercise utilized a compressed timeline that simulated approximately six months of emergency response activities over four days. This compression was achieved through the use of time jumps that allowed participants to experience different phases of emergency response, from initial detection and assessment through peak response activities and eventual de-escalation. The compressed timeline maintained the intensity and decision-making pressure characteristic of actual emergencies while enabling comprehensive testing of response capabilities.

The design incorporated both individual regional activities and coordinated national-level activities, testing both vertical coordination between national and regional levels and horizontal coordination among regions. This dual approach enabled assessment of the full range of coordination mechanisms that are essential for effective emergency response in Ethiopia's federal system.

Exercise Process

The exercise process was carefully structured to ensure systematic testing of all key capabilities while maintaining realism and engagement. The process began with comprehensive preparation activities that included scenario development, inject preparation, participant briefing, and technical setup.

The exercise was conducted using a hybrid approach that combined in-person activities at regional PHEOCs with virtual coordination mechanisms. This approach reflected the realities of emergency response in a geographically diverse country while testing the technological infrastructure and communication protocols essential for effective coordination.

The exercise utilized an inject-driven methodology, where pre-scripted scenario updates were delivered to participants at predetermined intervals. These injects were designed to simulate the flow of information and events that would occur during an actual emergency, requiring participants to make decisions, take actions, and coordinate responses based on evolving information.

Communication during the exercise utilized multiple channels including email, telephone, video conferencing, and messaging platforms. This multi-channel approach tested the redundancy and reliability of communication systems while reflecting the diverse communication needs of emergency response.

Participants

The exercise involved a comprehensive range of participants representing the full spectrum of Ethiopia's public health emergency response system. At the national level, participants included staff from the Ethiopian Public Health Institute's National PHEOC, representing all functional areas of the Incident Management System including command and control, operations, planning, logistics, and finance and administration.

Regional participation included representatives from all thirteen regional PHEOCs, with each region fielding teams that represented their local Incident Management System structure. Regional participants included PHEOC managers, surveillance focal persons, laboratory coordinators, risk communication specialists, case management experts, and logistics coordinators.

Government sector participation extended beyond health to include representatives from the National Disaster Risk Management Commission, Animal Health Institute, and other relevant ministries and agencies. This multi-sectoral participation was essential for testing the One Health approach and ensuring realistic simulation of inter-sectoral coordination.

International partner participation included representatives from the World Health Organization, Centers for Disease Control and Prevention, UK Health Security Agency, Ohio State University Global One Health Initiative, and other technical partners. These partners served in various capacities including exercise management team members, technical advisors, and observers.

The total number of participants exceeded one hundred individuals, representing one of the largest functional simulation exercises conducted in Ethiopia's public health sector. This broad participation enabled comprehensive testing of coordination mechanisms while building capacity across the entire system.

Exercise Management Team

The Exercise Management Team was structured to ensure effective oversight and evaluation of the exercise while maintaining the integrity of the simulation. The team included multiple levels of management and evaluation, from national coordination to regional facilitation.

At the national level, the Exercise Management Team included an Exercise Director responsible for overall strategic oversight and decision-making, Exercise Controllers who managed the flow of the exercise and ensured adherence to the scenario timeline, and Evaluators who assessed performance against predetermined criteria.

Regional Exercise Management Teams were established at each participating regional PHEOC, including regional controllers who facilitated local activities and ensured coordination with national-level activities, regional evaluators who assessed regional performance and documented lessons learned, and observers who provided additional perspectives on exercise conduct and outcomes.

The Exercise Management Team structure enabled comprehensive evaluation while maintaining clear separation between exercise management functions and participant activities. This separation was essential for ensuring objective evaluation and maintaining the realism of the simulation.

Exercise Conduction

The exercise was conducted over four intensive days, with activities beginning each day with briefings and ending with debriefing sessions. The daily structure included morning briefings that oriented participants to the day's activities and scenario updates, intensive exercise periods where participants responded to injects and coordinated activities, and evening debriefing sessions that captured immediate observations and lessons learned.

The exercise utilized a master scenario events list that provided the overall framework for scenario progression, while individual injects provided specific information and challenges that required participant response. The timing and delivery of injects were carefully managed to maintain appropriate pacing and ensure that participants had sufficient time to respond effectively while maintaining the pressure and urgency characteristic of actual emergencies.

Coordination between national and regional levels was maintained through regular video conferences, email communications, and telephone calls. These coordination mechanisms were themselves part of the exercise, testing the effectiveness of communication systems and protocols under simulated emergency conditions.

Documentation of exercise activities was maintained throughout the exercise period, including records of decisions made, actions taken, communications sent and received, and coordination activities conducted. This documentation provided the foundation for post-exercise evaluation and lesson identification.

Exercise Evaluation Method and Tool

The evaluation methodology was designed to provide comprehensive assessment of exercise performance while generating actionable recommendations for improvement. The evaluation approach incorporated multiple methods and perspectives to ensure thorough and objective assessment.

Structured evaluation criteria were developed based on the exercise objectives, with specific indicators and standards established for each area of assessment. These criteria provided the framework for systematic evaluation while ensuring consistency across different regions and functional areas.

Evaluation tools included standardized observation forms that enabled evaluators to systematically record observations and assess performance against predetermined criteria. These forms were designed to capture both quantitative measures of performance and qualitative observations about the effectiveness of procedures and coordination mechanisms.

The evaluation methodology incorporated multiple perspectives, including self-assessment by participants, observation by trained evaluators, and analysis of exercise documentation and communications. This multi-perspective approach provided a comprehensive view of exercise performance while identifying areas where different perspectives revealed different insights.

Post-exercise debriefing sessions were conducted at both regional and national levels, providing opportunities for participants to share their experiences, identify lessons learned, and contribute to the evaluation process. These debriefing sessions were structured to encourage honest reflection and constructive feedback while maintaining focus on system improvement rather than individual performance.

# Major Findings

Finding on Exercise Process

Strengths

- The exercise demonstrated exceptional commitment and engagement from participants across all levels, with regional PHEOCs showing remarkable dedication despite competing priorities and resource constraints. The hybrid exercise format proved highly effective, enabling broad participation while testing realistic communication and coordination mechanisms that would be utilized during actual emergencies.

- Communication systems and technologies generally functioned well throughout the exercise, with video conferencing capabilities enabling effective coordination between national and regional levels. The email-based inject delivery system worked efficiently, and most regions demonstrated good technical capacity for virtual coordination and information sharing.

- The exercise scenario was realistic and engaging, providing appropriate levels of challenge without overwhelming participants. The multi-outbreak approach successfully tested the system's capacity to manage complex emergencies while the compressed timeline maintained appropriate urgency and decision-making pressure.

- Exercise management and facilitation were generally effective, with clear communication of expectations and consistent delivery of injects. The Exercise Management Team structure enabled comprehensive oversight while maintaining separation between management and participant functions.

- Documentation and record-keeping during the exercise were generally good, providing sufficient information for evaluation and lesson identification. Most regions maintained appropriate records of decisions, actions, and communications throughout the exercise period.

Gaps

- Several regions experienced challenges with internet connectivity and technical infrastructure, affecting their ability to participate fully in virtual coordination activities. Some regions lacked adequate backup power systems, creating vulnerabilities during simulated extended response operations.

- Time management proved challenging in several instances, with some injects delivered too rapidly for effective response, particularly during the initial phases of the exercise. Lunch breaks were frequently shortened, affecting participant energy and engagement during afternoon sessions.

- Pre-exercise preparation varied significantly across regions, with some participants having limited prior exposure to simulation exercises. This affected their ability to engage effectively with the exercise format and respond confidently to scenario challenges.

- Communication protocols were not consistently followed, with some regions experiencing confusion about email addresses, group communications, and reporting procedures. The group email system experienced technical difficulties in some regions, affecting information flow.

- Resource allocation for the exercise was uneven, with some regions lacking adequate refreshments, accommodation, or logistical support for participants. This affected participant comfort and engagement, particularly during extended exercise sessions.

Finding Against Each Objective

Objective 1: Operationalization of Emergency Management Plans and Procedures

Strengths

- Most regions demonstrated good awareness of existing emergency plans and procedures, with participants referencing appropriate guidelines and protocols during their responses. The National PHEOC effectively utilized the Mpox response plan and prepared incident action plans that provided clear guidance for response activities.

- Several regions successfully activated alert modes and implemented pre-activation procedures in response to scenario developments. Risk assessments were conducted in multiple regions, demonstrating understanding of the importance of evidence-based decision-making in emergency response.

- Contingency planning was evident in several regions, with participants developing scenario-specific plans that addressed the unique challenges presented by the multi-outbreak situation. Standard operating procedures were referenced and utilized, though with varying degrees of consistency across regions.

- The exercise demonstrated that basic emergency management structures and procedures are in place and understood by key personnel. Most regions were able to implement some form of incident management system activation, even if not always following prescribed procedures exactly.

Gaps

- Consistent adherence to standard operating procedures was lacking across regions, with many participants not following step-by-step activation procedures as outlined in the PHEOC handbook. Risk assessment procedures were not consistently applied, with some regions proceeding with activation decisions without conducting formal risk assessments.

- Role clarity within the Incident Management System was problematic in several regions, with participants sometimes responding to injects outside their designated functional areas. This led to duplication of efforts and confusion about responsibilities during response activities.

- Pre-activation and activation procedures were not consistently followed, with some regions assuming activation without following prescribed notification and grading procedures. Incident grading and level of activation determination were frequently overlooked or inadequately documented.

- Many regions lacked updated hard copies of essential plans and procedures, relying instead on soft copies that might not be accessible during actual emergencies. Contingency plans were not consistently developed or attached by all functional pillars during the exercise.

Objective 2: Coordination and Collaboration Mechanisms

Strengths

- Coordination between national and regional PHEOCs was generally effective, with regular information sharing and communication maintained throughout the exercise. Most regions successfully participated in virtual coordination meetings and provided situational updates using standardized templates.

- Several regions demonstrated good internal coordination among Incident Management System sections, with effective information sharing and collaborative decision-making observed. Daily coordination meetings were conducted in some regions, facilitating information flow and coordinated planning.

- Partner engagement was evident in several regions, with participants recognizing the importance of multi-sectoral coordination and making efforts to involve relevant stakeholders in response planning. Some regions successfully engaged with international partners and demonstrated understanding of resource mobilization procedures.

- One Health coordination mechanisms were activated in multiple regions, with participants demonstrating awareness of the need for cross-sectoral coordination, particularly for zoonotic diseases like rabies. Task force meetings were conducted in some regions, bringing together human health, animal health, and other relevant sectors.

Gaps

- Inter-regional communication was largely absent, with limited evidence of coordination between neighbouring regions despite the cross-border nature of some scenario elements. This represents a significant gap in coordination mechanisms that could be critical during actual multi-regional emergencies.

- Partner engagement was inconsistent across regions, with many regions failing to actively involve key partners in response planning and coordination. Partner mapping and resource mobilization planning were inadequately addressed in most regions.

- One Health sector engagement was limited in scope, with environmental health sectors rarely included in coordination mechanisms. While human and animal health coordination was evident in some regions, comprehensive One Health approaches were not consistently implemented.

- Communication clarity and timeliness varied significantly, with some regions experiencing delays in information sharing and coordination. Standardized communication templates were not consistently used, affecting the quality and comparability of information products.

Objective 3: Information Sharing and Management

Strengths

- Several regions successfully prepared and shared Situation Reports (SITREPs) and Spot Reports (SPOTREPs) using appropriate templates and formats. Information products were generally shared with leadership and relevant stakeholders in a timely manner.

- The National PHEOC demonstrated strong information management capabilities, preparing comprehensive situation reports with graphical presentations and maintaining effective information flow to regional levels. Media scanning and event-based surveillance information was effectively managed and disseminated.

- Most regions successfully participated in national coordination meetings, presenting situational updates using standardized templates and contributing to shared situational awareness. Information sharing during virtual meetings was generally effective and well-organized.

- Documentation of response activities was maintained in most regions, providing records of decisions made and actions taken during the exercise. This documentation provided valuable information for evaluation and lesson identification.

- Information products were shared with appropriate stakeholders, including leadership, partners, and other relevant sectors. Most regions demonstrated understanding of the importance of information sharing for effective coordination and decision-making.

Gaps

- Standardized templates for SPOTREPs and SITREPs were not consistently used across regions, affecting the quality and comparability of information products. Some regions prepared information products in narrative form without utilizing structured formats that facilitate analysis and decision-making.

- Information sharing with One Health sectors and partners was inconsistent, with many regions failing to include relevant stakeholders in information dissemination. This limited the effectiveness of multi-sectoral coordination and response planning.

- Some regions did not prepare formal information products for unverified signals, missing opportunities to maintain situational awareness and facilitate verification processes. The distinction between SPOTREPs for unverified signals and SITREPs for verified signals was not consistently understood or applied.

- Information management systems and procedures varied significantly across regions, with some regions lacking systematic approaches to information collection, analysis, and dissemination. This affected the quality and timeliness of information products and decision-making processes.

Objective 4: PHEOC-to-PHEOC Communication and Technology Use

Strengths

- Most regions successfully utilized available communication technologies, including video conferencing, email, and telephone systems. Virtual coordination meetings were generally successful, with good participation and effective information sharing.

- The National PHEOC demonstrated excellent communication capabilities, maintaining effective coordination with multiple regions simultaneously and facilitating information sharing across the network. Communication infrastructure at the national level proved robust and reliable.

- Several regions had functional video conferencing capabilities that enabled effective participation in coordination meetings. Technical support and backup systems were available in most locations, ensuring continuity of communications during the exercise.

- Communication protocols were generally understood, with most participants able to utilize email systems, join virtual meetings, and participate in coordinated communications. The hybrid exercise format successfully tested communication systems under realistic conditions.

Gaps

- Internet connectivity issues affected several regions, limiting their ability to participate fully in virtual coordination activities. Slow internet connections and technical difficulties disrupted communication and coordination in some locations.

- Video conferencing capabilities were not available or functional in all regions, limiting their ability to participate effectively in visual coordination meetings. Some regions lacked adequate cameras, audio equipment, or technical support for video communications.

- Communication device quality varied significantly across regions, with some participants using personal devices that were not adequate for professional coordination activities. This affected the quality and reliability of communications during the exercise.

- Technical skills for utilizing communication technologies varied among participants, with some individuals requiring additional support to participate effectively in virtual coordination activities. This highlighted the need for enhanced technical training and support.

Objective 5: Public Health Response Strategy Designing Capacity

Strengths

- Surveillance systems were effectively enhanced in most regions, with participants demonstrating good understanding of the need for intensified surveillance during outbreak situations. Event-based surveillance and indicator-based surveillance were strengthened, and contact tracing activities were initiated where appropriate.

- Risk Communication and Community Engagement (RCCE) strategies were developed in several regions, with participants creating appropriate messages for community dissemination. Multiple communication channels were identified and utilized, including traditional media, social media, and community structures.

- Case management protocols were generally well understood and implemented, with participants identifying appropriate isolation facilities, referral pathways, and treatment protocols. Infection Prevention and Control (IPC) measures were appropriately considered and implemented in most regions.

- Laboratory coordination was effective in most regions, with appropriate sample collection and testing procedures implemented. Laboratory capacity was assessed and enhanced where necessary, and results were communicated effectively to support decision-making.

- Screening procedures were implemented at points of entry and health facilities, demonstrating understanding of the importance of early detection and prevention measures. Standard operating procedures for screening were generally followed where available.

Gaps

- Adherence to Standard Operating Procedures was not consistently demonstrated, with some regions implementing response measures without clear reference to established protocols. This affected the quality and consistency of response activities across regions.

- Laboratory Turn-Around Time (TAT) and sequencing information was not consistently monitored or reported, limiting the ability to assess laboratory performance and make evidence-based decisions about response activities.

- RCCE message development and dissemination strategies were not consistently implemented across all regions, with some regions lacking dedicated RCCE focal persons or adequate resources for community engagement activities.

- Case tracking and referral processes were not systematically implemented in all regions, affecting the ability to monitor patient outcomes and ensure appropriate continuity of care. Some regions lacked clear referral pathways and case tracking systems.

- Supply chain management for critical materials including Personal Protective Equipment (PPE) and medical supplies was inadequately addressed in several regions, creating potential vulnerabilities during extended response operations.

Objective 6: Implementation of One Health Approach

Strengths

- Several regions successfully activated One Health coordination mechanisms, bringing together human health, animal health, and other relevant sectors for coordinated response planning. Task force meetings were conducted in some regions, demonstrating understanding of the importance of multi-sectoral coordination.

- The National PHEOC effectively engaged animal health sectors in response planning, particularly for zoonotic diseases like rabies. Coordination with the Animal Health Institute was established and maintained throughout the exercise.

- Some regions demonstrated good understanding of the One Health approach and its relevance to the diseases included in the exercise scenario. Joint response actions were planned and implemented, showing practical application of One Health principles.

- Cross-sectoral communication was established in several regions, with information sharing between human health and animal health sectors. This facilitated coordinated assessment and response planning for zoonotic disease threats.

Gaps

- Environmental health sector engagement was consistently lacking across regions, with most One Health coordination focusing only on human and animal health sectors. This represents a significant gap in comprehensive One Health implementation.

- Detailed One Health action plans were not developed in most regions, limiting the effectiveness of cross-sectoral coordination and response activities. Joint planning and implementation procedures were not systematically established.

- One Health coordination mechanisms were not consistently established at all levels, with some regions lacking clear procedures for multi-sectoral coordination during emergencies. This affected the ability to implement comprehensive One Health approaches.

- Clarity of proposed One Health actions was limited in many regions, with participants understanding the concept but lacking specific procedures and protocols for implementation. This highlighted the need for enhanced One Health training and capacity building.

# Conclusion from the Findings

The ET MRR Functional Simulation Exercise revealed a public health emergency response system with significant strengths and important areas requiring improvement. The exercise demonstrated that Ethiopia has established a functional network of Public Health Emergency Operations Centers with dedicated personnel who are committed to emergency preparedness and response. The basic infrastructure for emergency coordination exists, and many of the fundamental procedures and protocols are understood and can be implemented by trained personnel.

The exercise confirmed that coordination mechanisms between national and regional levels are functional and can be effectively utilized during emergencies. Communication systems and technologies generally performed well, enabling information sharing and coordination across the country's diverse geographic and administrative landscape. The hybrid exercise format proved that virtual coordination mechanisms can supplement in-person activities, providing flexibility and resilience in emergency response operations.

However, the exercise also revealed significant gaps that could compromise the effectiveness of emergency response if not addressed. Inconsistent adherence to standard operating procedures represents a critical vulnerability that could lead to delayed or inappropriate responses during actual emergencies. The lack of systematic risk assessment procedures could result in inappropriate activation decisions or inadequate resource allocation during emergencies.

Coordination gaps, particularly the absence of inter-regional communication and inconsistent partner engagement, could limit the effectiveness of response to multi-regional or complex emergencies. The limited implementation of comprehensive One Health approaches represents a missed opportunity for more effective prevention and response to zoonotic diseases, which constitute a significant proportion of public health threats in Ethiopia.

Information management capabilities, while generally functional, showed significant variation in quality and consistency across regions. This could affect situational awareness and decision-making during actual emergencies, particularly in complex situations requiring coordinated response across multiple regions and sectors.

The exercise demonstrated that while basic emergency response capabilities exist, the system requires strengthening to ensure consistent, effective response to complex public health emergencies. The gaps identified are addressable through targeted training, capacity building, infrastructure improvement, and procedural refinement.

# Recommendations for the identified gaps

Based on the comprehensive evaluation of the exercise, several key recommendations emerge that address the identified gaps and build upon demonstrated strengths. These recommendations are organized by priority and focus on systemic improvements that will enhance Ethiopia's public health emergency preparedness and response capabilities.

- The highest priority recommendation is the development and implementation of a comprehensive training program for PHEOC personnel at all levels. This training should focus on standard operating procedures, simulation exercise methodology, and the practical application of emergency management principles. The training program should be standardized across all regions while allowing for adaptation to local contexts and should include regular refresher training to maintain competency levels.

- Strengthening adherence to standard operating procedures requires the development of simplified, user-friendly quick reference guides that can be easily accessed and utilized during emergencies. These guides should be available in both hard copy and electronic formats and should be regularly updated to reflect lessons learned and best practices. Regular drills and exercises should be conducted to reinforce familiarity with procedures and identify areas requiring improvement.

- Inter-regional communication mechanisms must be established and tested regularly to ensure effective coordination during multi-regional emergencies. This includes developing formal protocols for information sharing between regions, establishing communication channels that can be activated during emergencies, and conducting regular inter-regional coordination exercises to test and refine these mechanisms.

- Partner engagement requires systematic improvement through the development of comprehensive stakeholder mapping exercises, establishment of formal partnership agreements with key organizations, and regular coordination meetings to maintain relationships and update response plans. Partner engagement should be integrated into all aspects of emergency preparedness and response planning.

- One Health implementation requires enhanced training and capacity building to ensure comprehensive understanding and application of One Health principles. This includes developing One Health coordination mechanisms at all levels, establishing clear roles and responsibilities for different sectors, and creating joint planning and response procedures that integrate human health, animal health, and environmental health perspectives.

- Information management systems require standardization and enhancement to ensure consistent, high-quality information products that support effective decision-making. This includes implementing standardized templates for all information products, establishing quality assurance procedures for information collection and analysis, and providing training on information management principles and practices.

- Technology infrastructure requires investment and improvement to ensure reliable communication and coordination capabilities during emergencies. This includes upgrading internet connectivity in regions with inadequate capacity, ensuring backup power systems are available and functional, and providing adequate communication equipment for all PHEOC personnel.

- Risk assessment capabilities require strengthening through the development of standardized risk assessment tools and procedures, training personnel in risk assessment methodology, and establishing requirements for risk assessment documentation and review. Risk assessment should be integrated into all activation and response planning decisions.

- Laboratory coordination and capacity require enhancement to ensure timely and accurate diagnostic support for emergency response. This includes establishing clear procedures for sample collection and transportation, implementing monitoring systems for laboratory turn-around times, and strengthening laboratory capacity for priority pathogens.

- Supply chain management systems require development and testing to ensure adequate availability of critical supplies during emergencies. This includes establishing strategic stockpiles of essential supplies, developing distribution procedures that can be rapidly activated, and creating monitoring systems to track supply availability and utilization.

# Annexes

## Annex 1: Action Plan for Improvement of Identified Gaps

| S.No | Action Items | Responsible Body | Timeframe |
| --- | --- | --- | --- |
| 1 | Develop comprehensive PHEOC training curriculum covering standard operating procedures, simulation exercise methodology, and emergency management principles | EPHI in collaboration with WHO and CDC | 6 months |
| 2 | Conduct standardized PHEOC training for all regional personnel with certification requirements and regular refresher training | Regional Health Bureaus with EPHI support | 12 months |
| 3 | Develop simplified quick reference guides for all standard operating procedures in both hard copy and electronic formats | EPHI with regional input | 4 months |
| 4 | Establish formal inter-regional communication protocols and test through quarterly coordination exercises | EPHI with Regional Health Bureaus | 8 months |
| 5 | Conduct comprehensive stakeholder mapping and establish formal partnership agreements with key organizations | Regional Health Bureaus with EPHI guidance | 6 months |
| 6 | Develop One Health coordination mechanisms at national and regional levels with clear roles and responsibilities | EPHI, Animal Health Institute, Environmental Protection Authority | 10 months |
| 7 | Implement standardized information management templates and quality assurance procedures for all PHEOCs | EPHI with regional implementation | 5 months |
| 8 | Upgrade internet connectivity and communication infrastructure in regions with inadequate capacity | Ministry of Health with development partner support | 18 months |
| 9 | Establish backup power systems and ensure functionality testing at all PHEOC locations | Regional Health Bureaus with central support | 12 months |
| 10 | Develop standardized risk assessment tools and procedures with mandatory training for all PHEOC personnel | EPHI with WHO technical support | 6 months |
| 11 | Strengthen laboratory coordination procedures and implement turn-around time monitoring systems | EPHI with Regional Public Health Institutes | 8 months |
| 12 | Establish strategic supply stockpiles and develop rapid distribution procedures for critical emergency supplies | EPHI, Ethiopian Pharmaceutical Supply Service | 12 months |
| 13 | Conduct at least bi-annual functional simulation exercises at regional level to maintain competency and test improvements | Regional Health Bureaus with EPHI support | Ongoing |
| 14 | Develop and implement quality assurance procedures for all PHEOC activities with regular monitoring and evaluation | EPHI with regional participation | 6 months |
| 15 | Establish formal mentorship, experience sharing and technical support programs linking experienced PHEOCs with developing PHEOCs | EPHI coordination with regional implementation | 9 months |

## Annex 2: National Exercise Management Team

| S.no | Name | Role in the Exercise | Email | Phone number |
| --- | --- | --- | --- | --- |
| 1 | Ebise Abose | Exercise director | abosedjirata@yahoo.com | 92 913 6507 |
| 2 | Lijalem Getie | Facilitator | lijgetie@gmail.com | 910978773 |
| 3 | Assegid Tesfaye | Controller | assegidgidami@gmail.com | 91 358 7132 |
| 4 | Fikirte Girma | Evaluator | fgirma12@gmail.com | 91 135 1203 |
| 5 | Dr.Fikadu | Controller | adugnadadif@who.int | 911237039 |
| 6 | Dr.Degu Tolosa | Controller | Dagu.Tolossa@ukhsa.gov.uk | 915566320 |
| 7 | Dr.Motuma | Controller | motumad@africacdc.org | 910748411 |
| 8 | Mohamed | Facilitator |  | 911008851 |

## Annex 3: National Exercise participants

| S.N | Name | Role in the exercise | Email | Phone number |
| --- | --- | --- | --- | --- |
| 1 | Asfaw Degefu | Player | asfawwakene16@gmail.com |  |
| 2 | Addisu Daba | Player | adisemi2013@gmail.com |  |
| 3 | Medhaney | Player | medhanyeh@gmail.com |  |
| 4 | Dr. Moti | Player | motiedosa7@gmail.com |  |
| 5 | Jimmawork | Player | jimmawork@gmail.com |  |
| 6 | Dr. Habtamu | Player | solomonhabtamu2018@gmail.com |  |
| 7 | Temesgen Lemi | Player | temuteffera1993@gmail.com |  |
| 8 | Ayantu Gizachew | Player | ayugize@gmail.com |  |
| 9 | Frehiwot Mulugeta | Player | firehiwotmulugeta70@gmail.com |  |
| 10 | Zenebe Girma | Player | zenebegirma19@gmail.com |  |
| 11 | Lulit Hailu | Player | lulithailu2010@gmail.com |  |
| 12 | Melaku Abebe | Player | meleabe@gmail.com |  |
| 13 | Abdi Beker | Player | abhar2011@gmail.com |  |
| 14 | Fahim Mohamedsani | Player | mailfahmim@gmail.com |  |
| 15 | Ayalneh Fenta | Player | melessea@who.int |  |
| 16 | Gulilat | Player | guleeyn1973@gmail.com |  |
| 17 | Khalid Nassir | Player | kheludnassir@gmail.com |  |
| 18 | Dr.Abere Mekonin | Player | mam3nice3@gmail.com |  |
| 19 | Dr.Werku Fitisa | Player | workufitesa@yahoo.com |  |
| 20 | Bikila Diriba | Player | bik.deriba@gmail.com |  |
| 21 | Naod Birhanu | Player | naodberhanu1111@yahoo.com |  |
| 22 | Tegegne Mulu | Player | tegegne.mulu@gmail.com |  |
| 23 | Selamawit Gebreegziabher | Player | tdy7@cdc.gov |  |
| 24 | Getachew Buko | Player | getacho2013@gmail.com |  |
| 25 | Befikadu Ejigu | Player | bekiisrael1948@gmail.com |  |
| 26 | Etalem | Player |  |  |

## Annex 4: National exercise management team deployed to regions

| National EMT deployed to regions |  |  |  |  |
| --- | --- | --- | --- | --- |
| S.n | Name | Region | Email | Phone number |
|  | Ashenafi sisay | Gambella | ashesis@yahoo.com | 911045608 |
|  | Dr Aklesia Kassa | Dire Dawa | aklesiyakassahun@gmail.com | 912795316 |
|  | Gumi Abebe | Hareri | kenenisagumi@gmail.com | 911487115 |
|  | Tamiru Tadesse | Jijiga | tamirutola4@gmail.com | 921347503 |
|  | Dr Nathan Fikire | Afar | nathanfik2019@gmail.com | 937404991 |
|  | Asfaw Mengesha | South Ethiopia | asfaw21menge@gmail.com | 926462813 |
|  | Asaye Gojamie | Amhara | asaye2000@gmail.com | 913935040 |
|  | Abenezer Mamo | Tigray | abenezer628@gmail.com | 936454690 |
|  | Almaz Tadese | Sidama | almaztad81@gmail.com | 941413281 |
|  | Dr.Abdulhamid Nasir | AA | hamidnassir99@gmail.com | 911766830 |
|  | Solomon Berhanu | SWE | solo.berhanu@gmail.com | 913458961 |
|  | Dr Gezahegn Getachew | B/Gumuz | gglife2@gmail.com | 910800638 |
|  | Dr Ahmed | Oromia | mohammedahmedkeb0@gmail.com | 920033671 |
|  | Mideksa Kebede | Oromia | mideksakebede2017@gmail.com | 911914461 |

## Annex 5: Regional Exercise participants

| S.no | Name | Job position | Role in the Exercise | Email | Phone number | Region |
| --- | --- | --- | --- | --- | --- | --- |
| 1 | Jemal Siraj | PHEM Officer | Participants | j34siraj@gmail.com | 921550093 | Afar |
| 2 | Jemal Yusuf | PHEM Officer | Participants | Jyusuf29@gmail.com | 910537721 | Afar |
| 3 | Endries Hussen | PHEM Officer | Participants | hussenadem1234@gmail.com | 910947463 | Afar |
| 4 | Daniel Alemu | PHEM Officer | Participants | danielalemu1991@gmail.com | 912759936 | Afar |
| 5 | Sauliha Mohammed | PHEM Officer | Participants | sualihamohamed99@gmail.com | 921970037 | Afar |
| 6 | Fentahun Agegnehu | PHEM Officer | Participants | fentishmw@gmail.com | 928433987 | Afar |
| 7 | Mohammed Ali | PHEM Officer | Participants | mohammadali2778@gmail.com | 913340659 | Afar |
| 8 | Yesuf Ali | PHEM Officer | Participants | Yes42255b@gmail.com | 929404047 | Afar |
| 9 | Abdu Ali | PHEM Officer | Participants | rageabdu2008@gmail.com | 910691216 | Afar |
| 10 | Bizuayehu Shimakew | WHO, Surveillance officer | Participants | fbizuayhu@gmail.com |  | Afar |
| 11 | Kedir Ali | PHEM Officer | Participants | qalikadir420@gmail.com | 921548767 | Afar |
| 12 | Zeyine Yasin | PHEM officer | RCCE | zeyineyas84@gmail.com | 945010854 | Gambella |
| 13 | Helen Ataklity | PHEM officer | Surveillance | helux24@gmail.com | 935143500 | Gambella |
| 14 | Ageze Teshome | PHEM officer | Case Mangment | agegnehu1995@gmail.com | 996176970 | Gambella |
| 15 | Yasuf Yasin | PHEM officer | Surveillance | yesufyassin02@gmail.com | 911997732 | Gambella |
| 16 | Omod Omod | PHEM officer | Surveillance | omodopeno@yahoo.com | 905292239 | Gambella |
| 17 | Dr. Wawich Khor | PHEM officer | Surveillance | wechlare@gmail.com | 927544979 | Gambella |
| 18 | Thock Makuach | PHEM officer | Surveillance | thokmakuach@gmail.com | 091780 4777 | Gambella |
| 19 | Obang Opiew | PHEM officer | Surveillance | obangopiew12@gmail.com | 967124158 | Gambella |
| 20 | Meron Bekele | PHEM officer | Surveillance | meronbekele0916@gmail.com | 960241390 | Gambella |
| 21 | Akwoma Okugn | PHEM officer | Surveillance | akwomaokogn@gmail.com | 913451438 | Gambella |
| 22 | Dereje deschasa | PHEM officer | Participant | dere56dech@gmail.com | 906378974 | AA |
| 23 | Zerihun Alemu | PHEM officer | Participant | zerihunalm@gmail.com | 911882947 | AA |
| 24 | Deschasa nesga | PHEM officer | Participant | dechasanesga@gmail.com | 947954622 | AA |
| 25 | Bezabih kindu | PHEM officer | Participant | bezabihkindu@gmail.com | 911795707 | AA |
| 26 | Teshome nigussie | PHEM officer | Participant | teshenegussie@gmail.com | 923501060 | AA |
| 27 | Netsanet Kifle | PHEM officer | Participant | netse.kifle@gmail.com | 911057035 | AA |
| 28 | Dr zekirub fanta | Case management team lead | Participant | Kirubelfanta@gmail.com | 912449533 | AA |
| 29 | Asmamaw deguale | Case management | Participant | asmamawdeguale16@gmail.com | 920258354 | AA |
| 30 | Sintayehu dinku | IPC-WaSH focal | Participant | sintayehudinku2005@gmail.com | 912360384 | AA |
| 31 | Biniyam abebe | PHEM officer | Participant | binyamabebe4584@gmail.com | 912183269 | AA |
| 32 | Tibebe zeleke | Logistics and supply management | Participant | tzeleke198@gmail.com | 911857487 | AA |
| 35 | Shimelis Abebe | Surge staff | Surveillance | shimelsa74@gmail.com | 911982877 | SWE |
| 37 | Mintesnot Endashaw | Medical Service officer | Case managemnet | minteend30@gmail.com | 917758230 | SWE |
| 38 | Tewodros Yemane | Measles/VPD Consultant | Surveilance | tedyem8@yahoo.com | 914727278 | SWE |
| 39 | Belayneh Kassa | PHEM Officer | RCCE | belaynehk2018@gmail.com | 910495667 | SWE |
| 40 | Dr. Kidus Yergalem | PHEOC Manager |  | kidusyirgalem@gmail.com | 924098190 | Harari |
| 41 | Nuredin Abdulahi | PHEM Officer |  | nuredinphem2019@gmail.com | 935780823 | Harari |
| 42 | Biniyam Teshome | Surveillance Coordinator |  | biniyamtessema911@gmail.com | 913261959 | Harari |
| 43 | Fowzi Salih | PHEM Director |  | fowzisalih@gmail.com | 921857353 | Harari |
| 44 | Dr Kalkidan Eyasu | Case Management |  | kaltesfamadam@gmail.com | 972797345 | Harari |
| 45 | Marye Tilahun | IPC |  | maryetilahun@yahoo.com | 946037825 | Harari |
| 46 | Shimelis Gashaw | PHEOC TA (Planning) | Participant | shimelisgashaw23@gmail.com | 912292123 | Amhara |
| 47 | Sintayehu Fentaw | PHEOC TA (Planning) | Participant | sintayehuf@gmail.com | 912280059 | Amhara |
| 48 | Sefi Derib | Surveillance | Participant | sefiderib@gmail.com | 910064236 | Amhara |
| 49 | Tsehaynesh G/Eyesus | Laboratory | Participant | CV121950@gmail.com | 986609833 | Amhara |
| 50 | Mulat Hussien | Laboratory | Participant | mulathussien@gmail.com | 913364356 | Amhara |
| 51 | Wondwosen Yehualaw | IPC/WaSH | Participant | wondiyeyehualaw@gmail.com | 945931099 | Amhara |
| 52 | Etalie Andualem | RCCE | Participant | etalie16@gmail.com | 912844902 | Amhara |
| 53 | Tilahun Yimaldu | RCCE | Participant | tyredeat@gmail.com | 918764763 | Amhara |
| 54 | Biniam Kebede | RCCE | Participant | kebedebiniam29@gmail.com | 921669286 | Amhara |
| 55 | Sisay Awoke | Case Management | Participant | sisaya16@gmail.com | 931887333 | Amhara |
| 56 | Mahdi Osmael | Lab section chief head | player | mahadiius@gmail.com | 915749115 | Somali |
| 57 | Khalid Farah soyan | RCCE section head | player | khalidsoyan@gmail.com | 929293192 | Somali |
| 58 | Sada usman | RCCE member | player | saadaosman74@gmail.com | 913549134 | Somali |
| 59 | Amin Hassen | Case Mangement section head | player | Muddathir043@gmail.com | 915222848 | Somali |
| 60 | Medina Mukerem | Logistic and planning member | player | medummm@gmail.com | 912798523 | Somali |
| 61 | Farah Nafis | WASH /IPC | player | farahnafis@gmail.com | 910223703 | Somali |
| 62 | Seid SheikHassen | Surveillance member | player | seidhasan33@gmail.com | 915057058 | Somali |
| 63 | Halima Babyab | Case Mangement member | player | babyadh@who.int | 960403535 | Somali |
| 64 | Abduweli Mohamed | Surveillance section head | player | walisheekh70@gmail.com | 915068990 | Somali |
| 65 | Ahmed Soane | logistic and Planning section head | player | Soane6666@gmail.com | 913283285 | Somali |
| 66 | Abera Birhanu | PHEM Officer | Coordination | aberabrhn@gmail.com | 913582016 | B.Gumuz |
| 67 | Kelbessa Teferi | PHEM Officer | Surveillance & Lab | tokkon5@gmail.com | 913909037 | B.Gumuz |
| 68 | Asifaw Bessie | Clinical Officer | Case management | asfawbessie@yahoo.com | 913350278 | B.Gumuz |
| 69 | Kibur Atakilti | PHEM Officer | RCCE | atkltikibur@gmail.com | 930333291 | B.Gumuz |
| 70 | Eshetu Yimer | PHEM Officer | Evaluator | eshetuyimer66@gmail.com | 949055986 | B.Gumuz |
| 71 | Alemayehu Megerssa | PHEM Officer | IPC & WaSH | alexaso83@yahoo.com | 911073390 | B.Gumuz |
| 72 | Mustefa | Pharmacy | Logestic |  | 917420334 | B.Gumuz |
| 73 | Tariku Melese | PHEM officer | planning section | melesetariku@gmail.com | 911762564 | S.Ethiopia |
| 74 | Merihun Dawit | lab officer | lab unit | dmerihun2023@yahoo.com | 916833440 | S.Ethiopia |
| 75 | Temesgen Tariku | RDMC | planning section | temesgentariku70@gmail,com | 916330904 | S.Ethiopia |
| 76 | Tefera Filipos | logistics | logistics section | teferafiliphos@gmail.com | 941040953 | S.Ethiopia |
| 77 | chole chumbulo | finance officer | Finance section | cholezelo4@gmail.com | 916880714 | S.Ethiopia |
| 78 | wendiye beshir | PHEM officer | RCCE unit | wondiyeaychew@gmail.com | 913509849 | S.Ethiopia |
| 79 | Dr. geyeto gara | research directorate | case management and IPC | geyetog123@gmail.com | 916710597 | S.Ethiopia |
| 80 | Tamirat gezahegn | RDMC | Surveillance unit | tamiratgezahegn7st@gmail.com | 932573808 | S.Ethiopia |
| 81 | ዶ/ር ርእየ ኢሳያስ |  | Incident Manager | rieye_belay@trhb.giv.et | 932501042 | Tigray |
| 82 | ሚኪኤለ ሓጎስ |  | Deputy incident Manager | mike2721126@gmail.com | 932501042 | Tigray |
| 83 | አቶ መብራህቶም ሃፍተ |  | PHEOC Manager | mebhafte@gmail.com | 914503244 | Tigray |
| 84 | ሰለሞን ንጉሰ |  | IT Expert | solomon.niguse1219@gmail.com | 902524794 | Tigray |
| 85 | ፀጋይ ካሕሳይ |  | Data manager | tsegaye2010k@gmail.com | 914757427 | Tigray |
| 86 | ሰብለወንጌል ለገሰ |  | Surveillance, Lab & PoE | seblewengellegese@gmail.com | 911299514 | Tigray |
| 87 | ወ/ሮ ይርጋኣለም መለስ |  | Surveillance, Lab & PoE | ymeles2013@gmail.com | 914392599 | Tigray |
| 88 | ዶ/ር ኣርኣያ ግርማይ |  | Surveillance, Lab & PoE | arayagirma23@gmail.com | 914124307 | Tigray |
| 89 | ሓጎስ ሃይለስላሴ |  | Surveillance, Lab & PoE | hagoshaileslsie78@gmail.com | 910304222 | Tigray |
| 90 | አቶ ሓበን ሓለፎም |  | EBS, media scanning | habenhalefom@gmail.com | 914404630 | Tigray |
| 91 | አቶ በሪሁ መስፍን |  | Public Information Officer | mesfinberihu10@gmail.com | 941250028 | Tigray |
| 92 | አቶ ኪደ ተኽሉ |  | Case Management | kideybalh@gmail.com | 970482727 | Tigray |
| 93 | ተኽለወይኒ ሃይለ |  | Case Management | mhaile464@gmail.com | 985026087 | Tigray |
| 94 | ወ/ሮ ኣስኳል ግርማይ |  | IPC Unit | askual2003@gmail.com | 914745589 | Tigray |
| 95 | ባህረ ተካ |  | IPC Unit | bahre6236@gmail.com | 910196354 | Tigray |
| 96 | ነጋሲ ገ/መስቀል |  | RCCE Unit | negasigmeskeltrhb@gmail.com | 914776232 | Tigray |
| 97 | አቶ ኢብራሂም ሓሰን |  | RCCE Unit | ebroinitiative@gmail.com | 914747000 | Tigray |
| 98 | ሃይለ ፀጋይ |  | Planning section lead | hailets2012@gmail.com | 914700841 | Tigray |
| 99 | አቶ ወ/ገሪማ ገ/መድህን |  | Capacity Building Unit | welegerima21@gmail.com | 914757799 | Tigray |
| 100 | አቶ የማነ ሓዱሽ |  | Situation and documentation | yemane2818@gmail.com | 914732039 | Tigray |
| 101 | አቶ ግደይ ገ/ሊባኖስ |  | Resource Mobilization | gideylibanos@yahoo.com | 914002818 | Tigray |
| 102 | አቶ ያሬድ ተኽሉ |  | EMT- facilitator | yaredteklu5@gmail.com | 914728656 | Tigray |
| 103 | አቶ ተስፋይ ገ/ሂወት |  | EMT- observer | tesfayg55@gmail.com | 914788179 | Tigray |
| 104 | አቶ ሃይላይ ገ/ሔር |  | EMT - Controller | haylaywukro2016@gmail.com | 913455140 | Tigray |
| 105 | አቶ አፈወርቂ ተስፋሁነኝ |  | OneHealth/Surveillance | afom.te@gmail.com | 914035386 | Tigray |
| 106 | ኣባዲ ማቸ |  | logistics | abeapha47@gmail.com | 914546158 | Tigray |
| 107 | ሙሉ ገ/ሂወት | Finance and Admin | Finance and Admin | mulugebriehiwot2@gmail.com | 914042688 | Tigray |
| 108 | Tenaye Kebede | PHEM officer | Participant | tenukebed@gmail.com | 914730405 | Sidama |
| 109 | Dr Tamiru Funte | PHEM officer | Participant | tamirufunte3@gmail.com | 919684482 | Sidama |
| 110 | Muse Bututa | PHEM officer | Participant | musse20168@gmail.com | 916351468 | Sidama |
| 111 | Kifle Kilisa | PHEM officer | Participant | kiflemache@gmail.com | 916957540 | Sidama |
| 112 | Belete Girma | PHEM officer | Participant | beletegirma57@gmail.com | 923404879 | Sidama |
| 113 | Eyasu Daniel | PHEM officer | Participant | eyudararo7@gmail.com | 916138707 | Sidama |
| 114 | Asefa Bekele | PHEM officer | Participant | asseb709@gmail.com | 962241311 | Sidama |
| 115 | Haileyesus Ejigu | PHEM officer | Participant | haileyesusejigu9@gmail.com | 916648958 | Sidama |
| 116 | Dr Nigussie | PHEM officer | Participant | sebron@who.int | 924663366 | Sidama |
| 118 | Eyilachew Zenebe | PHEM officer | Participant | eyilachew81.zenebe@gmail.com | 910084891 | DD |
| 119 | Tesfaye Derressa | PHEM officer | Participant | tderessa74@gmail.com | 911930374 | DD |
| 121 | Alemheh Amsalu | PHEM officer | Participant | amsalu004@gmail.com | 909626781 | DD |
| 122 | Tilahun Bekele | IPC officer | Participant | arsemayene@yahoo.com | 915750748 | DD |
| 123 | Meaza Tilaye | PHEM officer | Participant | meazi209@yahoo.com | 912089059 | DD |
| 124 | Dagmawi Abebe | PHEM officer | Participant | dagimab99@gmail.com | 912439994 | DD |
| 125 | D/r Nejib usmael | Case mgt | Participant | najedire5@gmail.com | 961412056 | DD |
| 126 | Eliyas Abdureman | Logistic and supply | Participant | eliasabdu2018@gmail.com | 913296950 | DD |
| 127 | Mubarek Gobeze | Case mgt | Participant | mubarekgobeze56@gmail.com | 906420072 | DD |

## Annex 6: Exercise agenda

Ethiopian Public Health Institute

Agenda for Functional Simulation Exercise on Multiple Emergency Response

Exercise_ET_MRR_2025

Addis Ababa, Ethiopia

Date of exercise: 25-26 June 2025

| Day 1: (25 June 2025) |  |  |
| --- | --- | --- |
| Time Frame | Session | Who (responsible person) |
| 09:00AM – 09:10AM | Zoom link joining process | Participants |
| 9:10AM-9:20AM | Key note speech | WHO representative |
| 9:20AM-9:30AM | Key note speech | UKHSA representative |
| 09:30AM – 09:40AM | Official opening & welcome | Dr.Melkamu Abte, DDG EPHI |
| 09:40AM – 10:00AM | Exercise briefing: Presentation on what the simulation communication, exercise agenda | Lijalem G. |
| 10:00AM-12:30AM | Exercise conduct (STRATX) | National Exercise Controller |
| 12:30 AM– 1:30PM | Lunch break (PAUSEX) | Participants |
| 1:40PM – 4:30PM | Exercise conduct | National Exercise Controller |
| 4:40PM | End of day 1 (PAUSEX) | National Exercise controller |
| Day 2: (26 June 2025) |  |  |
| 9:00AM-12:30 | Continue exercise conduct | National Exercise controller |
| 12:30AM | ENDX | National Exercise controller |
| 12:30AM-1:00PM | Hot-wash | Each PHEOC (national & regional |
| Day 3: (27 June 2025) |  |  |
| 9:00AM-12:30AM | Debriefing presentation | National and regional evaluators using presentation template (10’ each) |
| 12:30 | Wrap up of the exercise | Exercise director |

## Annex 7: Budget for exercise conduct

| S.N | Activities | Number of participants | Number of conduct days | Role | Bed room | Total cost (USD) | Budget source |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Per diem for exercise management team | 12 | 4 | Facilitators | 0 | 1,440 | UKHSA |
| 2 | Per diem for exercise players | 60 | 4 | Players | 0 | 4,800 | UKHSA |
| 3 | Regional exercise management team | 28 | 4 | Facilitators | 4 | 2,800 | UKHSA |
| 4 | Refreshment for Exercise participants | 72 | 2 |  | 0 | 1,152 | EPHI |
| 5 | Lunch for exercise participants | 72 | 2 |  | 0 | 864 | EPHI |
|  | Total | 72 |  |  |  | 11,056 |  |

## Annex 8: Participant Feedback form

Evaluation for Fx of multi outbreaks

Date of exercise: ________________

Please provide your evaluation of the exercise in which you just participated.

Your feedback is essential for the improvement of future exercises.

On a scale of 1 to 5, where 1 means you do not agree at all with the statement and 5 means you strongly agree with the statement, please evaluate the exercise based on the following questions:

| Statement | Do not agree |  | → |  |  | Strongly agree |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1. The exercise was well structured and organized | 1 | 2 |  | 3 | 4 |  | 5 |
| 2. The scenario was realistic | 1 | 2 |  | 3 | 4 |  | 5 |
| 3. The briefing before the exercise was useful and prepared me for the exercise | 1 | 2 |  | 3 | 4 |  | 5 |
| 4. The exercise allowed us to test our response plans and systems | 1 | 2 |  | 3 | 4 |  | 5 |
| 5. The exercise improved my understanding of my role and function during an emergency response | 1 | 2 |  | 3 | 4 |  | 5 |
| 6. The exercise helped me to identify some of my strengths as well as some of the gaps in my understanding of response systems, plans and procedures | 1 | 2 |  | 3 | 4 |  | 5 |
| 7. At the end of the exercise, I think we are better prepared for a health emergency | 1 | 2 |  | 3 | 4 |  | 5 |

Based on the exercise, what are the main strengths and areas for improvement?

| Strengths |  |
| --- | --- |
| Areas for improvement |  |

Please share any recommendation(s) you have to improve similar exercises in the future.

Thank you!

## Annex 9: Exercise evaluation form for observer

Ethiopian Public Health Institute

Functional Simulation Exercise on Multiple Emergency Response

Exercise_ET_MRR_2025

Evaluation form for observer.

Date of exercise:

N.B.  Tick relevant box at right (Y= Yes P= Partially N= No)

| Observations |  |  |  |
| --- | --- | --- | --- |
| Were the infrastructure, systems, organogram, team(s) (composition and roles and responsibilities) effective for the function/operation being evaluated? Comment: | Y | P | N |
| Were there procedure(s) and protocol(s) relevant to the function/operation? Was it/were they effective? Was it/were they followed? Comment: | Y | P | N |
| Was the coordination and communication between members of the team(s) clear and effective? Comment: | Y | P | N |
| Did the actual outcomes match the expected outcomes? Please relate to specific outcomes. Comment: | Y | P | N |
| General comments: |  |  |  |